Albany Infant and Nursery School

Sustainability Plan 2025 – 27

| Date reviewed | Version | Adaptations | Staff member |
| --- | --- | --- | --- |
| Spring 25 | 1 | New plan | K O’Neill |

### Establishing our school baseline

| #### Action | #### Steps | #### Timeline for the action or expected completion date | #### Resources | #### Co-benefits #### (any cross over benefits with other goals or plans) | #### Tools, resources and information | #### Funding opportunities |
| --- | --- | --- | --- | --- | --- | --- |
| Understand school’s carbon footprint by identifying where emissions come from. | Use an online tool such as Keep Britain Tidy’s to get a breakdown of carbon emissions. | By September 2025 | #### Staff: Education staff, operational staff, senior leadership team #### Cost: Free if using resources provided | #### None | Count Your Carbon - Eco Schools (eco-schools.org.uk) Energy-walkabout-guide_Guide.pdf (southwarkclimatecollective.co.uk) | #### Get involved ¦ Climate Ambassadors |
| Understand school's waste by conducting a bin audit. | Conduct bin audit. Review findings and propose recommendations to reduce or recycle waste. | June 2025 – one month audit | Staff: Education staff, operational staff, senior leadership team Cost: Free if using above tools | None | How to do a plastic waste bin audit - Plastic Free July Climate Friendly Audit – Climate Friendly Schools | Free |
| Understand the curriculum by reviewing for climate change content. | Review curriculum to understand where climate change/ careers features/ could feature. | Review March 2026 | Staff: curriculum lead, HT | Air quality | Our City, our world Conceptual milestones And key vocabulary (ourcityourworld.co.uk) Tracked changes project | Free |
| Understand the pupil’s concerns around the environment | Conduct pupil voice to find out their concerns and how school can support their views | July 2025 | Staff: curriculum lead, HT |  |  |  |

### Decarbonisation

The following actions could help you reduce carbon emissions that are caused by your school.

| #### Action | #### Steps | #### Timeline for the action or expected completion date | #### Resources | #### Co-benefits #### (any cross over benefits with other goals or plans) | #### Tools, resources and information | #### Funding opportunities |
| --- | --- | --- | --- | --- | --- | --- |
| Assess how well we are using your existing heat system/s. | Check that the building/s management and heating systems are running efficiently and correctly. Explore options for training if needed. | October 2025 | Staff: Caretaker/ SBM | None | Zero Carbon Action Builder — Retrofit Action for Tomorrow |  |
| Reduce carbon emissions in our buildings by teaching lessons outside. | Plan a lesson outdoors. Make the most of your outdoor environments and bring students outside for lessons. | Weekly from May 2025 | Staff: Teachers Cost: Free | Climate Education and Green Careers | Teach Outdoors, Education through outdoor learning A Teachers Guide to Adapting Lesson Plans for Outdoor Learning (dbdplay.com) Institute for Outdoor Learning – Home (outdoor-learning.org) Welsh Harp Environmental Education Centre Schools & Training — Project Rewild | Free |
| Change behaviours in our communities by running a ‘Switch-off’ campaign. | Encourage students and staff to turn off lights and monitors. Provide information to parents/carers in your newsletters. | February 2026 | Staff: Education staff, operational staff, senior leadership team Cost: Free | Climate Education and Green Careers | Switch Off Fortnight 2024 - Teacher Guidance - Twinkl | Free |

### Action plan goal: biodiversity

These actions will help you improve habitat and biodiversity around your school.

| #### Action | #### Steps | #### Timeline for the action or expected completion date | #### Resources | #### Co-benefits #### (any cross over benefits with other goals or plans) (optional) | #### Tools, resources and information (optional) | #### Funding opportunities (optional) |
| --- | --- | --- | --- | --- | --- | --- |
| Increase our school’s knowledge of biodiversity by joining an online biodiversity network. | Sign up to Education Nature Park for more resources. | June 2025 | Staff: educational staff/ senior leadership team Cost: Free | None | Education Nature Park. | Free |
| Increase our school's knowledge of biodiversity by starting a gardening club. | Locate an area to garden. Advertise amongst pupils. Grow plants and get students involved in maintenance/ harvest. | September 2025 | Staff: Educational staff/ senior leadership team Cost: Free / low | Climate Education and Green Career | Simple gardening club ideas / RHS Campaign for School Gardening | Cleaner Greener Safer - Southwark Council |
| Increase biodiversity on school property by tree planting. | Select an area of school ground suitable for tree planting. Research and select suitable trees for the area. Plant more trees on school grounds. Educate staff and students on their maintenance. | November 2025 | Staff: Education staff, operational staff, senior leadership team, Cost Low | Resilience and adaptation | Trees for Schools ¦ Trees for Cities | Southwark School Trees Planting ¦ Street Trees for London (streettreesforliving.org) Southwark’s tree planting programme. Please contact trees.envl@southwark.gov.uk |
| Increase biodiversity on school property by rewilding areas of school's grounds. | Select an area of school ground suitable for rewilding. Decide what type of rewilding (wildflower field, pond, insect hotels etc.). Buy native plants, stop using chemicals/ pesticides. Let the area grow. Educate staff and students on their maintenance. | May half term 2025 | Staff: Education staff, operational staff, senior leadership team, students Cost: Varied depending on complexity of project | None | Operation Future Hope Seven simple ways to create a wildlife-friendly garden ¦ Natural History Museum (nhm.ac.uk) How to make your garden wilder ¦ Rewilding Britain | Southwark biodiversity fund - Southwark Council |

### Action plan goal: climate education and green career

| #### Action | #### Steps | #### Timeline for the action or expected completion date | #### Resources | #### Co-benefits #### (any cross over benefits with other goals or plans) (optional) | #### Tools, resources and information (optional) | #### Funding opportunities (optional) |
| --- | --- | --- | --- | --- | --- | --- |
| Share with staff and pupils what climate change action we are taking by promoting successes and achievements. | Assemblies, newsletters. Get students involved e.g. with planting or maintaining. | 1 day | Staff: Education staff, senior leadership team Cost: Free | Relevant to all action plan goals |  | Free |
| Increase our school's knowledge of climate change initiatives by joining a climate network. | Research networks and decide which is the best for your school to keep up to date with latest information and opportunities. Sign up to the network. Start engaging with network, attend meetings, read newsletters etc. | 1 day, then ongoing | Staff: Education staff, senior leadership team Cost: Free | None | Southwark Climate Action Schools. For more information please contact ClimateEmergency@southwark.gov.uk Home - Eco Schools (eco-schools.org.uk) UK Climate Change • Let's Go Zero (letsgozero.org) | Free |

### Resilience and adaptation

| #### Action | #### Steps | #### Timeline for the action or expected completion date | #### Resources | #### Co-benefits #### (any cross over benefits with other goals or plans) (optional) | #### Tools, resources and information (optional) | #### Funding opportunities (optional) |
| --- | --- | --- | --- | --- | --- | --- |
| Planning: Assess your school's risk and vulnerability to climate change. | Use tools to assess your climate risk. Vulnerability analysis to identify the most at-risk areas of the school, such as aging infrastructure or vulnerable student populations. | 2 months | Staff: Education staff, operational staff, senior leadership team Cost: Dependant on actions chosen | Baseline | Climate Risk Mapping - London Datastore This provides a map of your heat and flood vulnerability Local Climate Adaptation Tool (lcat.uk) This provides information on health and community impacts of weather hazards in your local area Adaptation Scotland Resources including workplace resilience to extreme weather in schools and lesson plans to engage students Climate Just maps Understand how health, social and economic inequality and other vulnerabilities impact your local risk. Local Authority Climate Service Understand weather impacts for your school and how Southwark is specifically at risk |  |
| Planning: create a climate adaptation plan. | Engage stakeholders to tailor CAPs based on specific school needs and local climate risks. Assess measures based on your climate risk profile, your available resources, and co-benefits. Begin with 'quick win' measures that require minimal investment and show immediate benefits to build momentum. Include measures to build adaptive capacity, for instance thinking about how you can showcase the benefits of a measure as an educational opportunity to teachers, pupils, and parents. | 6 months- 1 year | Staff: Education staff, operational staff, senior leadership team Cost: Dependant on actions chosen | None | WWF resources for planning Guidance from Lambeth Adaptation Scotland :: The Framework - this guide from Scotland provides a framework for organisations including schools to develop their plans |  |
| Planning: Create policy to relax dress code in periods of hot weather. | Encourage pupils to wear loose, light-colored clothing. Sunhats. Sunscreen. Teachers should also encourage children to take off their jumpers. | 1 day | Staff: Education staff, senior leadership team Cost: Free | Climate Education and Green Careers | Hot weather and heatwaves: guidance for schools and other education settings – The Education Hub (blog.gov.uk) | Free |

### Active and sustainable travel

| #### Action | #### Steps | #### Timeline for the action or expected completion date | #### Resources | #### Co-benefits #### (any cross over benefits with other goals or plans) (optional) | #### Tools, resources and information (optional) | #### Funding opportunities (optional) |
| --- | --- | --- | --- | --- | --- | --- |
| Encourage active travel by providing cycle to work scheme for school staff. | Enrol your school in the cycle to work scheme. Promote amongst staff. | January 2026 | Staff: Education staff, senior leadership team Cost: Free to sign up | Air quality | Cycle2Work |  |
| Encourage active travel by providing walking buses. | Create a walking bus to school. | September 2026 | Staff: Education staff, senior leadership team Cost: Free | Air quality | How to: organise a walking bus to school (globalactionplan.org.uk) | Walking and Cycling Grants London - Groundwork |

### Action plan goal: air quality

These actions relate to directly improving air quality in and around the school for the benefit of pupils, staff, and parents and carers.

| #### Action | #### Steps | #### Timeline for the action or expected completion date | #### Resources | #### Co-benefits #### (any cross over benefits with other goals or plans) (optional) | #### Tools, resources and information (optional) | #### Funding opportunities (optional) |
| --- | --- | --- | --- | --- | --- | --- |
| Planning: Create an asthma friendly school plan. | Collect a register of all pupils with asthma. Create a school wide emergency asthma plan . Choose an asthma lead. Adopt a policy for inhaler techniques and emergency treatment. Create a system for identifying children who are missing school because of asthma. | 1 week, ongoing | Staff: Education staff, operational staff, senior leadership team Cost: Free | Resilience and Adaptation | Asthma friendly schools - Transformation Partners in Health and Care | Free |

### Action plan goal: waste, consumption and recycling

These actions seek to reduce waste and consumption and improve recycling within the school.

| #### Action | #### Steps | #### Timeline for the action or expected completion date | #### Resources | #### Co-benefits #### (any cross over benefits with other goals or plans) (optional) | #### Tools, resources and information (optional) | #### Funding opportunities (optional) |
| --- | --- | --- | --- | --- | --- | --- |
| Encourage reuse by running second-hand uniform event. | Run a uniform event at school for second hand uniform exchange and purchase. | June annually December annually | Staff: Education staff, senior leadership team Cost: Free | None | Uniformd | Free |
| Increase recycling by using recycled paper. | Review the school’s procurement policy and ensure paper purchased is recycled. | April 2026 | Staff: Education staff, operational staff, senior leadership team Cost: Low | None |  |  |
| Increase recycling by improving recycling facilities in the school. | Ensure that all classrooms have a recycling bin. Recruit dedicated recycling monitors to support staff and students. | June 2025 | Staff: Education staff, operational staff, senior leadership team Cost: Low | None |  |  |

### Food

| #### Action | #### Steps | #### Timeline for the action or expected completion date | #### Resources | #### Co-benefits #### (any cross over benefits with other goals or plans) #### (optional) | #### Tools, resources and information (optional) | #### Funding opportunities (optional) |
| --- | --- | --- | --- | --- | --- | --- |
| Increase our school's knowledge of food by running a sustainable food campaign at school. | Develop a campaign and link this with other national campaigns. Work with farm to fork – tesco | 2 months - ongoing | Staff: All school staff Cost: Free | Climate Education | Use resources from national campaigns such as WRAP’s Love Food Hate Waste campaign Run Food Waste Action Week with support from WRAP Contact School Food Matters for support to promote healthy and sustainable food | Free |